## Tracker
Week | Dates | Phase | ID | Task | Owner | Deliverable | Status | Notes
1 | Jul 20-26 | Define | 1.1 | Kickoff: survey insights + Empathy_canvas walkthrough | Echo | 30-min walkthrough | Done
1 | Jul 20-26 | Define | 1.2 | Converge: pick 1 primary + 1 secondary persona; problem statements via PHV template | All | Rationale + Skeleton s2 | Done
1 | Jul 20-26 | Define | 1.3 | Hypothesis + value proposition (fill PHV template) | Yiran | Filled PHV canvas | Dropped
1 | Jul 20-26 | Define | 1.4 | Goal statement (Ideate template) | Echo | Goal statement | Done
1 | Jul 20-26 | Define | 1.5 | Medical accuracy pass on selected personas + journeys | Shengxuan | Reviewed canvases | Dropped
1 | Jul 20-26 | Define | 1.6 | Figma setup: structure, tokens, accessibility checklist | Echo | Figma workspace ready | In progress
1 | Jul 20-26 | Define | 1.7 | Confirm mid-pre date & format with PwC | Echo | Date locked | Done | w3
2 | Jul 27-Aug 2 | Ideate/Lo-fi | 2.1 | Goal Statements + Crazy Eights workshop | All | HMW list + sketches | Done
2 | Jul 27-Aug 2 | Ideate/Lo-fi | 2.2 | IA + User flow: Log Event -> Timeline -> Summary | Shengxuan | Flowchart | In progress
2 | Jul 27-Aug 2 | Ideate/Lo-fi | 2.3 | Lo-fi wireframes, 5 locked screens | Echo | Lo-fi set in 04_design | Not started
2 | Jul 27-Aug 2 | Ideate/Lo-fi | 2.4 | Doctor-summary content model (bilingual field spec) | Shengxuan | Summary field spec | Not started
2 | Jul 27-Aug 2 | Ideate/Lo-fi | 2.5 | Competitor Audit | Yiran | Sheet | Done
3 | Aug 3-9 | Hi-fi + Mid-pre | 3.1 | Hi-fi design system + Home & Timeline screens | Echo | Figma frames | In progress
3 | Aug 3-9 | Hi-fi + Mid-pre | 3.2 | Mid-pre deck (CN): research -> problem -> lo-fi -> next | Yiran | Deck in collab/ | Done
3 | Aug 3-9 | Hi-fi + Mid-pre | 3.2b | CN versions of mid-pre canvases (persona, journey, empathy map) | Yiran | CN canvas exports | Done
3 | Aug 3-9 | Hi-fi + Mid-pre | 3.3 | Mid-pre rehearsal + MID-PRESENTATION (Fri Aug 7, TBC) | All | Delivered mid-pre | Done
3 | Aug 3-9 | Hi-fi + Mid-pre | 3.4 | Recruit 5-7 usability-test participants (Q11 pool) | Shengxuan | Confirmed list | Blocked
4 | Aug 10-16 | Hi-fi | 4.1 | Remaining several hi-fi screens + clickable prototype | Echo | Figma prototype link | In progress
4 | Aug 10-16 | Hi-fi | 4.2 | Real NF2 medical content into screens | Shengxuan | Content in Figma | Done
4 | Aug 10-16 | Hi-fi | 4.3 | Accessibility review of hi-fi | Echo | Review report | Not started
4 | Aug 10-16 | Hi-fi | 4.4 | Usability test plan + accessible task script | Echo | Test script | In progress
5 | Aug 17-23 | Test/Iterate | 5.1 | Run 5 moderated usability tests | Shengxuan | Notes per participant | Not started
5 | Aug 17-23 | Test/Iterate | 5.2 | Synthesize findings -> P0/P1/P2 fix list | Echo | Findings report | Not started
5 | Aug 17-23 | Test/Iterate | 5.3 | Iterate P0 fixes in prototype | Echo | Updated prototype | Not started
6 | Aug 24-30 | Finalize | 6.1 | Product roadmap 1-pager (community/research/records) | Echo | Roadmap 1-pager | Not started
6 | Aug 24-30 | Finalize | 6.2 | Final defense deck (CN) | Shengxuan | Deck v1 in collab/ | Not started
6 | Aug 24-30 | Finalize | 6.3 | Design documentation package (CN + EN) | All | Doc package | Not started
6 | Aug 24-30 | Finalize | 6.4 | Retro + September defense rehearsal schedule | All | Rehearsal schedule | Not started

## Summary
MediPort - PwC 6-Week Plan (Jul 20 - Aug 30, 2026)
Mid-presentation | Fri Aug 7 (placeholder - confirm with PwC)
Final defense | September, date TBD
Weekly sync | Sunday evening, 60 min
Echo capacity | Full Week 1; 5-8 hrs/wk from Jul 27 (semester)
Locked scope | 5 screens: Home, Log Event, Timeline, Generate Summary, Summary view; AI ingestion roadmap-only
Tasks by owner
Echo | 12
Yiran | 4
Shengxuan | 7
All | 5
Done / total | 10 / 28
How to use: update Status (dropdown) on Tracker. Owner colors: blue=Echo, green=Yiran, gold=Shengxuan, purple=All. Source: 01_planning/2_PwC_6Week_Plan.md